## PROJECT NAME INDEX
# | PROJECT NAME | DATES FOUND IN CHAT | SOURCE | IDENTITY / NOTES
1 | Bosswear website | 18 Nov 2025 | iBarry pricing chat | 22 Nov 2025: domain name requested; Barry said wait for client feedback and improve design if they proceed.
2 | Sow African Hair Braiding website | 20 Dec 2025 – 24 Feb 2026 | iBarry pricing chat | 9 Feb: privacy policy and terms/SMS consent text requested; 24 Feb: booking emails were bouncing and email/SMS delivery was tested.
3 | Mother's Love HHC website | 8 Feb – 8 Jun 2026 | iBarry pricing chat | 8 Feb project introduced; 12–16 Feb preview links shared; March client feedback; 29 Apr domain/hosting discussion; May–Jun revisions and deployment; 5 Jun video hidden pending consent.
4 | LinZ / Fottal.com caregiving website | 27 Mar – 21 May 2026 | iBarry pricing chat | 3 Apr payment confirmation; 14 May Fottal.com renewal/source code discussions; 16 May payment confirmation; 21 May domain/DNS conflict described.
5 | Unnamed client website / international expansion | 6–15 Mar 2026 | iBarry pricing chat | 6 Mar requirements missing; 9 Mar meeting notes; 11 Mar detailed requirements document; 12 Mar client said price was too much; 14 Mar $3.5k discussed/accepted by team.
6 | iBarry x Car Rental Platform | 15–18 Aug 2026 | iBarry pricing chat | 15 Aug meeting scheduled; 17 Aug meeting notes shared; 18 Aug peer-to-peer proposal document appears in nearby discussion, but relationship between projects is uncertain.
7 | iBarry peer-to-peer application / service support | 18 Aug – 2 Oct 2026 | iBarry pricing chat | 18 Aug proposal called too expensive; 29 Aug proposal/services documents forwarded; 19 Sep pricing/support discussion; 2 Oct client decision still pending.
8 | Barry's personal real-estate domain | 8–15 Jun 2026 | iBarry pricing chat | 8 Jun initial request; 9 Jun clarified domain only for existing site; 10 Jun price; 11 Jun promise to pay; 15 Jun changed desired domain to ibarryrealty.com.
9 | iBarryRealtor.com website | 19 Sep – 12 Oct 2026 | iBarry pricing chat | 19 Sep website request and scope; 21 Sep tagline/contact email; 5 Oct pricing discussion; 6 Oct final $500 agreement/payment schedule; 12 Oct preview URL shared.
10 | Haulers Haven application / platform | 28 Oct 2025 – 19 Jan 2026 | Dev Team chat | 28 Oct approved login animation; 23 Nov and 30 Nov meetings; 2–14 Dec progress and Gemini API access; 6 Jan Maps renewal; 11–22 Jan appointment and SMS feature requests; 19 Jan card removed from backend.
11 | iBarry Marketing website update | 1 Nov 2025 – 24 Jan 2026 | Dev Team chat | 1 Nov content supplied; 24 Jan ibarrymarketing.com provided as terms-and-conditions/business URL during Twilio setup.
12 | Fottal website (overlaps earlier Fottal/LinZ record) | 13 Nov 2025 – 21 May 2026 (combined evidence) | Dev Team chat | 13 Nov 2025 Fottal design feedback; later activity captured in existing iBarry pricing chat.
13 | Sow African Hair Braiding website | 14 Nov 2025 – 24 Feb 2026 (combined evidence) | Dev Team chat | 14 Nov requirements and assets; 15 Nov prototype link; 17 Nov booking/stylist functionality; 8 Dec prototype praised; 10–11 Dec image/deployment; 21–24 Jan Booksy, prices and SMS setup.
14 | AsmadGroup.com website reactivation / redesign | 17–20 Nov 2025 | Dev Team chat | 17 Nov website reactivation request; 18 Nov domain expired/email failure; 19 Nov redesign discussion; 20 Nov urgent need for domain to function.
15 | Custom blazer e-commerce website (client unnamed) | 18 Nov 2025 | Dev Team chat | 18 Nov requirements: online orders and blazer customization. Not enough evidence to connect this to Mr Al's separate e-commerce meeting.
16 | Mr Al's e-commerce website | 21 Nov 2025 | Dev Team chat | 21 Nov 2025: project named and meeting discussed. Could be related to blazer e-commerce, but the chat does not confirm this.
17 | Construction company website (client unnamed) | 21 Nov 2025 | Dev Team chat | 21 Nov 2025: first meeting proposed, then second meeting discussed. On 24 Nov Barry clarified Ghana contact was a former boss and the meeting was for requirements only, not pricing.
18 | Haulers Haven website servicing | 23–25 Nov 2025 | Dev Team chat | 23 Nov meeting; 24 Nov servicing scope; 25 Nov client may have chosen old developer, so continuation uncertain.
19 | Durachemgh.com website servicing | 24 Nov 2025 | Dev Team chat | 24 Nov 2025: domain shared and Barry described work as basically servicing the website.
20 | Rosella.ng website / skincare brand | 24 Nov – 11 Dec 2025 | Dev Team chat | 24 Nov URL shared; 1 Dec prioritized; 4 Dec two prototype links; 11 Dec feedback pending and client sorting matters.
21 | Maya / Posh Beauty 224 skincare website | 1–11 Dec 2025 | Dev Team chat | 1 Dec skincare project and Maya meeting notes; 8 Dec Posh Beauty social links and requirements; 10 Dec image replacement; 11 Dec prototype link and launch discussion.
22 | John Maher website (business name undecided) | 11 Dec 2025 | Dev Team chat | 11 Dec 2025: meeting notes shared, name not finalized, website requested; email sent; SMS provider pricing requested.
23 | Diallo Telly Institute app | 27–28 Aug 2026 | Dev Team chat | 27 Aug client was calling and had a Saturday meeting; 28 Aug call requested with client; app not yet built according to developer.
24 | Skincare website / profile website (Maya meeting notes; likely Posh Beauty) | 1–8 Dec 2025 | Dev Team chat | 1 Dec description and 8 Dec Posh Beauty social links; treated as same project as Maya/Posh Beauty pending confirmation.

## Summary
iBarry Projects — Full Dated Record
Source | WhatsApp export: “iBarry pricing” (messages from 18 Nov 2025 through 12 Oct 2026).
Projects identified | 9
Chronological events | 54
Payment / promise events | 7
Important | Quotes, promises, and agreement amounts are not proof of payment. Amounts are kept in the currency stated in chat.
Receipt status | Two transfers were explicitly acknowledged (3 Apr and 16 May 2026), but neither amount is stated in the text. A $125 image was mentioned on 6 May in Mother's Love context; its exact purpose is unclear.
Caution | Some projects may overlap or be ambiguously identified, especially the unnamed March client, Mother's Love vs. Fottal caregiving work, and car-rental vs. peer-to-peer app.
Privacy | Credentials and unrelated private account information from the chat were intentionally excluded.
Date coverage | Dates are converted from the WhatsApp export date stamps. Where the source only gives a month/period, that is marked in the project register rather than inventing an exact date.
Additional source added | Dev Team.zip — WhatsApp export, 28 Oct 2025 through 28 Aug 2026
Additional named/possible projects | 23
Combined master project entries | 33
New dated timeline events | 33
Payment/accounting caution | Dev Team export contains price quotes, renewal needs, payment promises, and a likely Twilio-credit purchase; these are not all confirmed client payments. See Dev Team Payments and All Projects Master.

## Project Register
Project ID | Project | First/last dated activity | Scope / deliverables | Quotes / prices and dated details | Currency | Payment status from chat | Other dated milestones / notes | Date coverage | Overall status
P-01 | Bosswear website | 18 Nov 2025 | Website design/development; prototype, brand-matched styling, article publishing/marketing features discussed. | Initial pricing moved through $1,500, $1,200, $1,300, then Barry said he would charge client $1,500; on 18 Nov reduced request to $750 + $50 maintenance. On 19 Nov Barry offered to add $150 to the $750. | USD | No confirmed payment in chat. Final price and whether project proceeded are unclear. | 22 Nov 2025: domain name requested; Barry said wait for client feedback and improve design if they proceed. | Nov 2025 | Quote/negotiation only
P-02 | Sow African Hair Braiding website | 20 Dec 2025 – 24 Feb 2026 | Website updates, domain/hosting, SMS booking/customer notifications, privacy policy, terms, booking email troubleshooting. | 20 Dec: €60 domain + €70 hosting stated (message says €120 total/year, arithmetic mismatch). 12 Jan: $130 domain+hosting discussed. 15 Jan: $70 hosting if domain already owned; domain $60. | EUR / USD as written | No explicit payment receipt located. Website work and email/booking troubleshooting are documented. | 9 Feb: privacy policy and terms/SMS consent text requested; 24 Feb: booking emails were bouncing and email/SMS delivery was tested. | Dec 2025–Feb 2026 | Quote; work/update activity
P-03 | Mother's Love HHC website | 8 Feb – 8 Jun 2026 | Caregiving agency website; pages, content, testimonials, imagery/video, SEO/meta title, service-area updates, email, deployment and domain. | 5 Jun: Barry said he urgently needed $250 from the client. 6 May: Barry shared an image and wrote “This is $125”; surrounding context discusses Mother's Love domain, but purpose/recipient of the $125 is not explicit. Domain/hosting quote not clearly isolated from other work. | USD | $250 is a request for money, not proof of receipt. $125 image is a payment-related clue, but not enough to confirm what it paid for. 3 Jun Barry said client had not paid him yet. | 8 Feb project introduced; 12–16 Feb preview links shared; March client feedback; 29 Apr domain/hosting discussion; May–Jun revisions and deployment; 5 Jun video hidden pending consent. | Feb–Jun 2026 | Active work; payment unclear
P-04 | LinZ / Fottal.com caregiving website | 27 Mar – 21 May 2026 | Caregiving website; reviews, insurance wording, service areas, content revisions, domain, deployment and source-code handover. | 3 Apr: labor amount discussed as 1,200,000 GNF (Barry) vs 1,250,000 GNF (Sekou). 29 Apr: 2,500,000 GNF labor + $120 domain/hosting quoted. Earlier figures conflict and are not reconciled. | GNF + USD | 3 Apr transfer explicitly acknowledged after Barry asked if it was received; amount/purpose not definitively tied to a specific quote. 16 May transfer explicitly acknowledged; amount unclear. 6 May $125 image is more likely in Mother's Love context and should not be assumed to be this project. | 3 Apr payment confirmation; 14 May Fottal.com renewal/source code discussions; 16 May payment confirmation; 21 May domain/DNS conflict described. | Mar–May 2026 | Some receipt acknowledgements; amounts unverified
P-05 | Unnamed client website / international expansion | 6–15 Mar 2026 | Requirements analysis and project overview; client reportedly wanted to expand to other countries including the UK. | 14 Mar: $3,500 price asked about and team reportedly accepted to avoid losing the client. 15 Mar: additional work/extension would have extra cost, not quantified. | USD | No payment or deposit receipt confirmed. Client/project identity is not clear from the chat. | 6 Mar requirements missing; 9 Mar meeting notes; 11 Mar detailed requirements document; 12 Mar client said price was too much; 14 Mar $3.5k discussed/accepted by team. | Mar 2026 | Quote reportedly accepted; payment unconfirmed
P-06 | iBarry x Car Rental Platform | 15–18 Aug 2026 | A car-rental platform was discussed; meeting scheduled and meeting notes shared. The chat does not prove whether it is the same as the peer-to-peer app project. | No price explicitly captured in the visible messages summarized here. | Not stated | No payment evidence identified. | 15 Aug meeting scheduled; 17 Aug meeting notes shared; 18 Aug peer-to-peer proposal document appears in nearby discussion, but relationship between projects is uncertain. | Aug 2026 | Project discussion; identity/quote uncertain
P-07 | iBarry peer-to-peer application / service support | 18 Aug – 2 Oct 2026 | App proposal; UI/UX; operating costs separated from servicing; training and post-launch support; first three months of maintenance requested free. | 19 Sep: $250/year flat support fee proposed. Operational costs were to be separate. Client requested first 3 months free maintenance after completion plus training. | USD | No confirmation that the $250 annual support fee was paid or that a final support contract was accepted. | 18 Aug proposal called too expensive; 29 Aug proposal/services documents forwarded; 19 Sep pricing/support discussion; 2 Oct client decision still pending. | Aug–Oct 2026 | Support quote; payment unconfirmed
P-08 | Barry's personal real-estate domain | 8–15 Jun 2026 | Initially requested barryibrahim20.com for existing WordPress/MLS-connected realtor site; later changed preferred domain to ibarryrealty.com. | 10 Jun: $60 domain + $70 annual hosting = $130. Barry said he would send money on 11 Jun and again on 15 Jun. | USD | Promised payment only; no receipt confirmation identified. | 8 Jun initial request; 9 Jun clarified domain only for existing site; 10 Jun price; 11 Jun promise to pay; 15 Jun changed desired domain to ibarryrealty.com. | Jun 2026 | Payment promised; receipt unconfirmed
P-09 | iBarryRealtor.com website | 19 Sep – 12 Oct 2026 | Realtor website; WordPress, responsive design, SEO/blog/neighborhood pages, Bright MLS via IDX, buy/rent/sell paths, contact forms and property search. | 6 Oct: $800 quote; Barry countered $400; after negotiation final agreed development fee $500. Payment plan discussed: 60% when ready + 10% each Friday for 4 installments. Approx. $30/month for IDX/MLS was discussed separately. | USD | Final $500 agreement documented, but no actual payment receipt identified. The installment plan was proposed by Barry; payments not confirmed. $30/month is a recurring estimated operating cost, not confirmed paid. | 19 Sep website request and scope; 21 Sep tagline/contact email; 5 Oct pricing discussion; 6 Oct final $500 agreement/payment schedule; 12 Oct preview URL shared. | Sep–Oct 2026 | Agreed fee; payment unconfirmed

## Dated Timeline
Date | Project / possible link | Event category | What happened (dated chat evidence) | Amount / price detail | Status / interpretation
18 Nov 2025 | Bosswear website | Pricing | Sekou shared invoice; Barry said price was too high and discussed affordable portfolio-building pricing. | $1,500 proposed by Sekou; $1,200 Barry counter; $1,300 Sekou response; Barry said he would charge client $1,500. | Negotiation only
18 Nov 2025 | Bosswear website | Pricing revision | Barry asked to reduce development price to $750 and add $50 maintenance. | $750 + $50 maintenance proposed. | Proposal only
19 Nov 2025 | Bosswear website | Pricing contribution | Barry said he would add $150 to the $750 price. | $150 proposed contribution; not a receipt. | Proposal only
22 Nov 2025 | Bosswear website | Scope / domain | Barry said he was not impressed with the existing site and wanted stronger brand colors and an article-writing option if the client proceeded. | No new amount. | Client decision pending
4 Dec 2025 | Unspecified website (likely Sow African Hair Braiding, confirm) | Price request | Barry asked for website cost; team asked which website. Project identity is not fully clear in this exchange. | No amount. | Unclear
20 Dec 2025 | Sow African Hair Braiding / likely referred client | Domain + hosting | Barry asked for domain/hosting cost; Sekou quoted €60 domain and €70 hosting, while stating €120 total/year. | €60 + €70; stated total €120 (arithmetic discrepancy). | Quote only
12 Jan 2026 | Sow African Hair Braiding | Domain/hosting + SMS | Barry asked again for costs and said he would handle SMS; Sekou said $130 for domain and hosting. | $130 quoted. | Quote only
15 Jan 2026 | Sow African Hair Braiding | Cost breakdown | Sekou said hosting was $70 and domain $60; domain could be transferred if already owned. | $70 hosting; $60 domain. | Quote only
9 Feb 2026 | Sow African Hair Braiding | Website legal pages | Barry requested Privacy Policy and Terms & Conditions pages with SMS consent/STOP/HELP language. | No amount. | Scope/update
8 Feb 2026 | Mother's Love HHC | Project introduced | Barry shared the agency link and requested a website for the caregiving agency. | No amount. | Project request
9–16 Feb 2026 | Mother's Love HHC | Development / preview | Requested creative design and updates; preview links were shared on 12 Feb and 16 Feb. | No amount. | Work in progress
24 Feb 2026 | Sow African Hair Braiding / booking email setup | Technical support | Booking emails were bouncing; team tested email and SMS delivery. | No amount. | Support activity
28 Feb 2026 | Sow African Hair Braiding / other pending work | Payment follow-up | Sekou followed up; Barry said he was handling some things and asked for more time. Context does not identify the exact invoice conclusively. | No amount. | Payment delayed / project link uncertain
6 Mar 2026 | Unnamed client website | Requirements | Team said they still had not received client requirements agreed the prior day. | No amount. | Requirements pending
9 Mar 2026 | Unnamed client website | Meeting notes | Barry shared meeting notes from 7 Mar. | No amount. | Project discovery
10 Mar 2026 | Unnamed client website | Pricing process | Barry asked what the team would charge; team said it would first prepare a project overview. | No amount. | Quote not ready
11 Mar 2026 | Unnamed client website | Requirements analysis | Detailed client requirements document shared and sent for validation; Barry said client confirmed. | No amount. | Requirements confirmed
12 Mar 2026 | Unnamed client website | Client response | Barry said client thought the proposed price was too high. | No amount recorded in this message. | Negotiation
14 Mar 2026 | Unnamed client website | Price proposal | Barry asked if $3,500 was acceptable; said client wanted possible expansion to other countries such as the UK. Sekou said team would accept to avoid losing the client. | $3,500 proposed/reportedly accepted by team. | Payment not confirmed
15 Mar 2026 | Unnamed client website | Scope change | Barry asked about additional cost for extra work; team said there would be an additional cost but did not quantify it. | Additional cost not specified. | Open item
18–25 Mar 2026 | Mother's Love HHC / possible second site discussion | Client feedback | Client feedback included name clarity, image/video use, transitions and content changes; Barry said stock images might need to be purchased. | Image licensing cost not stated. | Scope/change requests
26 Mar 2026 | Mother's Love HHC | Delivery urgency / payment concern | Barry asked to finish the site and obtain domain/hosting; team asked about remaining money. Barry asked to obtain domain/hosting for Mother's Love too. | No confirmed amount paid in this message. | Payment / launch pending
27 Mar 2026 | Mother's Love HHC | Content revisions | Changes requested to service areas, insurance wording and images. | No amount. | Scope/update
3 Apr 2026 | LinZ / Fottal.com caregiving site | Labor price discussion | Barry stated 1.2m GNF; Sekou stated 1m250k GNF. Later that evening Barry asked if transfer had arrived; Sekou checked international account and confirmed receipt. | 1,200,000 vs 1,250,000 GNF disputed; transfer amount not independently stated. | Receipt acknowledged; amount unclear
3 Apr 2026 | LinZ / Fottal.com caregiving site | Website revisions | Requested review label changes, removal of a review, service-area order and tagline update. | No new amount. | Scope/update
9 Apr 2026 | LinZ / Fottal.com or related work | Service reactivation | Barry asked to reactivate the site; Sekou said payments were late and ongoing services incurred costs. | No amount. | Payment delay noted
28 Apr 2026 | LinZ / Fottal.com | Launch request | Barry asked to get the domain and make the site live. | No amount. | Launch pending
29 Apr 2026 | LinZ / Fottal.com | Price clarified | Sekou stated domain and hosting were $120 and labor was 2,500,000 GNF; Barry planned to send $120 Friday and the remainder the following Friday. | $120 + 2,500,000 GNF. | Payment promised, not confirmed
1 May 2026 | LinZ / Fottal.com or related caregiving work | Payment promise | Barry apologized and said he wanted to send domain/hosting money and handle the rest the following Friday. | No new amount. | Promise only
6 May 2026 | Mother's Love HHC (context suggests this project) | Domain / payment image | Barry suggested mothersloveinc.com as the domain and shared an image, writing “This is $125.” Exact payment purpose/recipient cannot be verified from the text export. | $125 shown/reported by Barry; payment not independently confirmed. | Possible payment; allocation uncertain
7–8 May 2026 | Mother's Love HHC | Homepage content | Barry asked to put client material on the homepage; team said it was done. | No amount. | Work update
8–9 May 2026 | Mother's Love HHC / related invoice | Payment follow-up | Sekou asked for payment; Barry said he would send it in a few hours. No receipt confirmation immediately follows in this section. | No amount. | Promise only
13–14 May 2026 | LinZ / Fottal.com | Ownership / domain renewal | Barry requested GitHub repo ownership and domain purchase details; requested Fottal.com renewal; source code zip shared. | No amount. | Transfer/renewal task
15 May 2026 | LinZ / Fottal.com or related work | Payment promise | Team asked for payment update; Barry said he would send it during the day. | No amount. | Promise only
16 May 2026 | LinZ / Fottal.com or related work | Payment receipt | Barry said he had just sent payment; Sekou replied that he received it. | Amount/currency not stated. | Receipt acknowledged; do not assign amount
18–21 May 2026 | LinZ / Fottal.com | Hosting / DNS troubleshooting | Team discussed where the site was hosted and a domain already managed by another Netlify team; access/domain release was needed. | No amount. | Technical issue
2–8 Jun 2026 | Mother's Love HHC | Website revisions / deployment | Client requested new imagery, service content and meta-title changes; Barry said he had not yet been paid on 3 Jun; deployment and revisions continued. | 5 Jun Barry urgently requested $250 from client; this is not proof of receipt. | Payment outstanding per Barry
8 Jun 2026 | Barry's personal real-estate domain | Domain request | Barry requested barryibrahim20.com for his existing real-estate site. | No price yet. | Request
9 Jun 2026 | Barry's personal real-estate domain | Scope clarification | Barry clarified he only wanted a domain connected to an existing WordPress/MLS-enabled site; a more luxurious redesign was optional. | No price yet. | Scope clarified
10 Jun 2026 | Barry's personal real-estate domain | Quote | Sekou quoted $60 for the domain and $70 for one year of hosting. | $130 total implied. | Quote only
11 Jun 2026 | Barry's personal real-estate domain | Payment promise | Barry said he would send the money the following day. | $130 quote context. | Promise only
15 Jun 2026 | Barry's personal real-estate domain | Domain changed | Barry said he was sending the money that night and changed preference to ibarryrealty.com. | $130 quote context. | Payment not confirmed
15 Aug 2026 | iBarry x Car Rental Platform | Meeting | Barry shared meeting details for a car-rental platform discussion. | No amount recorded. | Project discussion
17 Aug 2026 | iBarry x Car Rental Platform | Meeting notes | Barry shared meeting notes from the prior meeting. | No amount recorded. | Project discussion
18 Aug 2026 | iBarry peer-to-peer application (relationship to car-rental platform uncertain) | Proposal | Peer-to-peer app proposal document shared; Barry said it was too expensive and asked what a client might pay; UI/UX support was discussed. | No price amount captured in these messages. | Proposal under negotiation
29 Aug 2026 | iBarry peer-to-peer application | Proposal documents | Service and application proposal documents were forwarded again. | No amount stated in messages. | Proposal documents
19 Sep 2026 | iBarry peer-to-peer application | Support and operating costs | Barry asked for exact monthly operational costs separate from servicing, and requested 3 months of free servicing after completion plus training. Sekou proposed $250/year support. | $250/year support proposal; operations separate. | Quote only
2 Oct 2026 | iBarry peer-to-peer application | Client decision pending | Barry said client would decide the following night about support. | $250/year proposal context. | Decision not confirmed
19 Sep 2026 | iBarryRealtor.com | Website request | Barry requested a realtor website and described property search through MLS; said he expected to pay about $30 monthly for that service. | Approx. $30/month IDX/MLS operating cost. | Operating estimate, not confirmed paid
21 Sep 2026 | iBarryRealtor.com | Brand / contact details | Barry provided tagline “A Marketer’s Eye. A Realtor’s Commitment” and an iBarryRealtor email address. | No amount. | Brand setup
5 Oct 2026 | iBarryRealtor.com | Pricing discussion | Team realized price had not been settled before work started; design described as interactive. | No amount yet. | Pricing pending
6 Oct 2026 | iBarryRealtor.com | Final development fee | Sekou quoted $800; Barry countered $400; after negotiation Barry settled on $500 and team accepted. Barry suggested 60% when ready and 10% each Friday for four installments. | Final agreed development fee: $500. Proposed payment schedule totals 100%; no receipts confirmed. | Agreed fee; payment unconfirmed
6 Oct 2026 | iBarryRealtor.com | Scope | Front office for clients/visitors and back office for administrators discussed; realtor website scope included MLS/IDX and SEO. | Included in project fee subject to final scope. | Scope
12 Oct 2026 | iBarryRealtor.com | Preview link | Preview URL shared: ibarryrealtor.vercel.app. | No amount. | Build activity

## Payments & Promises
Date | Project / possible link | Amount | Currency | Event type | Evidence from chat | Accounting note / follow-up
3 Apr 2026 | LinZ / Fottal.com or related caregiving work | Not stated | Not stated | Transfer sent and acknowledged | Sekou first said it had not arrived, then confirmed receipt after checking international account. | Do not assume it equals 1.2m or 1.25m GNF labor figure without transfer proof.
6 May 2026 | Likely Mother's Love HHC based on surrounding messages | $125 | USD (as described) | Payment image/message; purpose unclear | Barry wrote “This is $125” with an image while discussing Mother's Love domain and client follow-up. | Need inspect original image/receipt to identify payer, recipient, purpose and whether paid.
16 May 2026 | LinZ / Fottal.com or related work | Not stated | Not stated | Transfer sent and acknowledged | Barry said he had just sent it; Sekou replied “I've received.” | Could be related to a prior outstanding amount; do not assign amount without receipt.
11 Jun 2026 (promised) | Barry's personal real-estate domain | $130 quoted | USD | Payment promise | Barry said he would send money tomorrow. | No receipt confirmation found.
15 Jun 2026 (promised) | Barry's personal real-estate domain | $130 quoted | USD | Payment promise / domain changed | Barry said he was sending the money that night, then changed domain preference to ibarryrealty.com. | No receipt confirmation found.
5 Jun 2026 | Mother's Love HHC | $250 requested | USD | Urgent request to client | Barry said he needed $250 from them that day to make a payment. | This is a request, not proof the client paid.
6 Oct 2026 | iBarryRealtor.com | $500 agreed fee | USD | Agreement / payment plan | Barry proposed 60% when ready, then 10% every Friday for four installments. | Not a receipt. Plan is proposal only.

## Scope & Deliverables
Project | Scope / work items evidenced in chat | Dates mentioned
Bosswear website | Brand-matched design; prototype; article publishing/marketing option; website development. | 18 Nov 2025; 22 Nov 2025
Sow African Hair Braiding website | Website updates; SMS functionality; Privacy Policy and Terms & Conditions; booking/email delivery troubleshooting. | 20 Dec 2025; 12–15 Jan 2026; 9 Feb 2026; 24 Feb 2026
Mother's Love HHC website | Caregiving agency pages; testimonials; imagery/video; service area and insurance wording; meta title; domain; deployment. | 8 Feb–8 Jun 2026
LinZ / Fottal.com caregiving website | Caregiving website revisions; reviews; service-area list; tagline; domain/hosting; GitHub/source-code handover; DNS/hosting troubleshooting. | 27 Mar–21 May 2026
Unnamed client website | Requirements analysis; project overview; international expansion/UK considered; extra scope may cost more. | 6–15 Mar 2026
iBarry x Car Rental Platform | Meeting and meeting notes; project identity/relationship to peer-to-peer app uncertain. | 15–17 Aug 2026
iBarry peer-to-peer application | Application proposal; UI/UX; operational costs vs servicing; training; three months free maintenance; $250/year support proposal. | 18 Aug–2 Oct 2026
Barry's personal real-estate domain | Existing WordPress/MLS site; domain only initially; changed from barryibrahim20.com to ibarryrealty.com; hosting quote also given. | 8–15 Jun 2026
iBarryRealtor.com website | Realtor website; WordPress; mobile speed; SEO; Philadelphia neighborhood pages; articles; Bright MLS/IDX search; buy/rent/sell flows; front-office and back-office. | 19 Sep–12 Oct 2026

## Quotes & Price History
Project | Date | Amount / quote | Context | Status
Bosswear | 18 Nov 2025 | $1,500 | Initial price mentioned by Barry for client-facing pricing | Not final; negotiation continued
Bosswear | 18 Nov 2025 | $1,200 | Barry counterproposal | Superseded
Bosswear | 18 Nov 2025 | $1,300 | Sekou proposal | Superseded
Bosswear | 18 Nov 2025 | $750 + $50 maintenance | Reduced price requested by Barry | Proposal; outcome/payment unconfirmed
Bosswear | 19 Nov 2025 | $150 extra contribution | Barry offered to add $150 on top of $750 | Proposal only
Sow African Hair Braiding | 20 Dec 2025 | €60 domain + €70 hosting; stated total €120/year | Quote in chat; arithmetic does not match components | Quote only
Sow African Hair Braiding | 12 Jan 2026 | $130 domain + hosting | Price restated in USD | Quote only
Sow African Hair Braiding | 15 Jan 2026 | $70 hosting; $60 domain | Breakdown if domain already owned/needed transfer | Quote only
Unnamed client website | 14 Mar 2026 | $3,500 | Barry asked if team accepted; Sekou said team would accept | Reportedly accepted by team; no payment evidence
LinZ / Fottal.com | 3 Apr 2026 | 1,200,000 GNF vs 1,250,000 GNF | Conflicting labor figures stated by Barry and Sekou | Unreconciled
LinZ / Fottal.com | 29 Apr 2026 | $120 domain/hosting + 2,500,000 GNF labor | Sekou's stated quote | Payment promised; not confirmed
Mother's Love HHC | 6 May 2026 | $125 | Barry described an image as “This is $125” | Exact purpose/receipt not independently verified
Mother's Love HHC | 5 Jun 2026 | $250 | Barry requested urgently from client | Request, not receipt
Barry's personal real-estate domain | 10 Jun 2026 | $60 domain + $70 hosting/year = $130 | Quote for domain/hosting | Promised 11/15 Jun; receipt unconfirmed
iBarry peer-to-peer app | 19 Sep 2026 | $250/year support | Annual support/service fee; operating costs separate; 3 months free maintenance requested | Proposal; payment unconfirmed
iBarryRealtor.com | 6 Oct 2026 | $800 initial quote | Sekou's quoted development fee | Superseded
iBarryRealtor.com | 6 Oct 2026 | $400 counteroffer | Barry's counteroffer | Superseded
iBarryRealtor.com | 6 Oct 2026 | $500 final agreed fee | Barry's final price and team acceptance | Agreed, payment unconfirmed
iBarryRealtor.com | 19 Sep 2026 / Oct 2026 | Approx. $30/month IDX/MLS | Recurring third-party operating cost estimate | Not part of confirmed developer payment; payment unconfirmed

## Dev Team Project Register
ID | Project name | Date range | Scope / deliverables | Price / cost details | Currency | Payment status | Dated milestones / notes | Date coverage | Overall status
D-01 | Haulers Haven application / platform | 28 Oct 2025 – 19 Jan 2026 | Approved login opener animation; application development; AI integration (Gemini); Google Maps; Apple authentication; service appointment booking and pricing; client account/API setup. | No project fee amount visible in this chat. Google Maps service expired 6 Jan 2026; renewal needed, amount not stated. Twilio/SMS service setup discussed Jan 2026. | USD / not stated | No confirmed project-fee receipt. Barry said payment would be made the next day on 21 Jan (purpose unclear). On 22 Jan he said Twilio credits purchase was done after being asked to buy credits; amount not stated. | 28 Oct approved login animation; 23 Nov and 30 Nov meetings; 2–14 Dec progress and Gemini API access; 6 Jan Maps renewal; 11–22 Jan appointment and SMS feature requests; 19 Jan card removed from backend. | Oct 2025–Jan 2026 | Active development / payment unclear
D-02 | iBarry Marketing website update | 1 Nov 2025 – 24 Jan 2026 | Update company website content/branding; business description, manifesto, services, mission, vision and values; site URL later used for Twilio compliance/terms URL. | No development price or payment stated in this chat. | Not stated | No payment evidence in this chat. | 1 Nov content supplied; 24 Jan ibarrymarketing.com provided as terms-and-conditions/business URL during Twilio setup. | Nov 2025–Jan 2026 | Website update / payment not discussed
D-03 | Fottal website (overlaps earlier Fottal/LinZ record) | 13 Nov 2025 – 21 May 2026 (combined evidence) | UI/UX corrections, caregiving website updates, reviews, services, domain/hosting, deployment and source-code/domain handover. | Dev Team chat names Fottal on 13 Nov 2025 but no amount in this chat. Earlier iBarry pricing workbook has later price/payment details; see existing Fottal/LinZ project record. | GNF + USD in earlier chat | No additional payment receipt identified in Dev Team chat. Use existing workbook's 3 Apr and 16 May 2026 receipt acknowledgements, amounts unclear. | 13 Nov 2025 Fottal design feedback; later activity captured in existing iBarry pricing chat. | Nov 2025–May 2026 | Merged/overlapping project; avoid double-counting
D-04 | Sow African Hair Braiding website | 14 Nov 2025 – 24 Feb 2026 (combined evidence) | Salon website, gallery/images, stylist selection, booking, admin image uploads, domain, hosting, hairstyle prices and duration, SMS notifications and booking emails. | Dev Team chat states domain renewal for 1 year as 800,000 GNF on 17 Nov, but context likely another site/reactivation and should not be assigned to Sow without confirmation. Earlier chat quoted domain/hosting in EUR/USD. | GNF / EUR / USD in chats | No confirmed payment receipt for the domain/hosting in Dev Team chat. On 22 Jan Barry said Twilio credits purchase was done; likely SMS credits, amount not stated. | 14 Nov requirements and assets; 15 Nov prototype link; 17 Nov booking/stylist functionality; 8 Dec prototype praised; 10–11 Dec image/deployment; 21–24 Jan Booksy, prices and SMS setup. | Nov 2025–Feb 2026 | Active website work; payment unclear
D-05 | AsmadGroup.com website reactivation / redesign | 17–20 Nov 2025 | Website/domain reactivation; email delivery issue; possible redesign to satisfy client. | 800,000 GNF for one year was quoted on 17 Nov in the preceding exchange; likely domain renewal/reactivation but chat context does not explicitly attach it beyond that site discussion. | GNF | No confirmed payment receipt. On 20 Nov Barry said Asmad Group was waiting for an urgent payment and wanted the domain functional. | 17 Nov website reactivation request; 18 Nov domain expired/email failure; 19 Nov redesign discussion; 20 Nov urgent need for domain to function. | Nov 2025 | Reactivation/possible redesign; payment unclear
D-06 | Custom blazer e-commerce website (client unnamed) | 18 Nov 2025 | E-commerce site to sell blazers with custom logo/text/image uploaded by customers. | No price stated. | Not stated | No payment evidence in this chat. | 18 Nov requirements: online orders and blazer customization. Not enough evidence to connect this to Mr Al's separate e-commerce meeting. | Nov 2025 | Requirements only / client identity unclear
D-07 | Mr Al's e-commerce website | 21 Nov 2025 | E-commerce website; a meeting was scheduled to discuss project requirements. | No price stated. | Not stated | No payment evidence in this chat. | 21 Nov 2025: project named and meeting discussed. Could be related to blazer e-commerce, but the chat does not confirm this. | Nov 2025 | Discovery/meeting only
D-08 | Construction company website (client unnamed) | 21 Nov 2025 | Website requirements discovery; one or more client meetings planned. | No price stated. | Not stated | No payment evidence in this chat. | 21 Nov 2025: first meeting proposed, then second meeting discussed. On 24 Nov Barry clarified Ghana contact was a former boss and the meeting was for requirements only, not pricing. | Nov 2025 | Discovery only
D-09 | Haulers Haven website servicing | 23–25 Nov 2025 | Website servicing and maintenance discussed separately from the application; requirements/images and domain/hosting were discussed. | No price stated. Domain and hosting were to be discussed after client feedback; no amount captured. | Not stated | No payment receipt identified. | 23 Nov meeting; 24 Nov servicing scope; 25 Nov client may have chosen old developer, so continuation uncertain. | Nov 2025 | Potentially separate servicing engagement; outcome unclear
D-10 | Durachemgh.com website servicing | 24 Nov 2025 | Existing website servicing/maintenance. | No price stated. | Not stated | No payment evidence in chat. | 24 Nov 2025: domain shared and Barry described work as basically servicing the website. | Nov 2025 | Servicing discussion only
D-11 | Rosella.ng website / skincare brand | 24 Nov – 11 Dec 2025 | Website prototypes, image replacement, domain/hosting purchase and launch; skincare profile site with articles discussed. | No price stated in Dev Team chat. | Not stated | Barry said invoices had been sent and responses were pending on 26 Dec, but no specific payment receipt is linked to Rosella. | 24 Nov URL shared; 1 Dec prioritized; 4 Dec two prototype links; 11 Dec feedback pending and client sorting matters. | Nov–Dec 2025 | Prototype delivered; launch/payment unclear
D-12 | Maya / Posh Beauty 224 skincare website | 1–11 Dec 2025 | Simple skincare profile website with article page; image replacement; deployment; domain/hosting and launch; strategy work referenced. | No price stated. | Not stated | No payment receipt identified. Invoices for clients generally were said to be sent 26 Dec, not specifically assigned to this project. | 1 Dec skincare project and Maya meeting notes; 8 Dec Posh Beauty social links and requirements; 10 Dec image replacement; 11 Dec prototype link and launch discussion. | Dec 2025 | Prototype delivered; payment/launch unclear
D-13 | John Maher website (business name undecided) | 11 Dec 2025 | Website requested while client was still deciding business name; email and SMS notification costs discussed. | No website fee stated. Paid SMS service required; exact service cost not stated. | Not stated | No payment evidence identified. | 11 Dec 2025: meeting notes shared, name not finalized, website requested; email sent; SMS provider pricing requested. | Dec 2025 | Requirements/quote pending
D-14 | Diallo Telly Institute app | 27–28 Aug 2026 | App project; client asked whether to begin training on how to operate it, but developer clarified the app had not yet been built and a process meeting was needed. | No price stated. | Not stated | No payment evidence in chat. | 27 Aug client was calling and had a Saturday meeting; 28 Aug call requested with client; app not yet built according to developer. | Aug 2026 | Requirements/process not finalized
D-15 | Skincare website / profile website (Maya meeting notes; likely Posh Beauty) | 1–8 Dec 2025 | A profile website with an articles page was requested for a skincare business in Guinea. Likely the same project later associated with Posh Beauty 224; kept as an alias rather than a separate project in master list. | No price stated. | Not stated | No payment evidence. | 1 Dec description and 8 Dec Posh Beauty social links; treated as same project as Maya/Posh Beauty pending confirmation. | Dec 2025 | Alias/identity linked with caveat

## Dev Team Timeline
Date | Project name / possible link | Event | What the chat records | Amount / price | Interpretation / status
28 Oct 2025 | Haulers Haven application | Approved animation | Remi’x shared that Haulers Haven approved an animation to use as a login opener before the home page. | No amount stated. | Approved creative asset; not a payment.
1 Nov 2025 | iBarry Marketing website | Website content/update | Barry requested an update to ibarrymarketing.com and shared new brand positioning, services, mission, vision and values. | No amount stated. | Scope request.
13 Nov 2025 | Fottal website | Design feedback | Barry flagged UI/UX mistakes for Fottal. | No amount stated. | Work request; same/overlapping Fottal project in earlier workbook.
14 Nov 2025 | Sow African Hair Braiding | Project kickoff | Website requested urgently; flyer, fonts, colors, logo, content and wireframe shared. | Domain/hosting cost requested, no quote in this message. | Requirements and assets supplied.
15 Nov 2025 | Sow African Hair Braiding | Prototype | sow-braiding.netlify.app shared. | No amount stated. | Prototype link shared.
17 Nov 2025 | Sow African Hair Braiding | Booking feature | Barry requested ability for customers to choose a stylist and book online. | No amount stated. | Scope update.
17 Nov 2025 | Website reactivation (likely AsmadGroup; confirm) | Renewal quote | Sekou said the client had not renewed the domain and stated 800,000 GNF for one year. Exact project attachment is not fully explicit in the adjacent text. | 800,000 GNF / one year. | Quote only; not proof of payment.
18 Nov 2025 | Custom blazer e-commerce website | Requirements | Separate e-commerce site requested for selling blazers with customizable logo image/text. | No price stated. | Client unnamed; relation to Mr Al's e-commerce is uncertain.
19 Nov 2025 | AsmadGroup.com | Redesign request | Barry reported client dissatisfaction and asked whether the team could redesign the website; Barry offered to bear some cost. | No amount stated. | Redesign discussion.
20 Nov 2025 | AsmadGroup.com | Domain/payment urgency | Barry said Asmad Group was waiting for an urgent payment and wanted the domain functional. | No amount stated. | Client's payment need, not a receipt to development team.
21 Nov 2025 | Mr Al's e-commerce website | Discovery meeting | Meeting planned for the e-commerce website. | No amount stated. | Discovery only.
21 Nov 2025 | Construction company website | Discovery meeting | Meeting proposed for a construction company's website; a second meeting was also discussed. | No amount stated. | Discovery only.
23 Nov 2025 | Haulers Haven | Project meeting | Barry announced a Haulers Haven meeting. | No amount stated. | Project activity.
24 Nov 2025 | Haulers Haven website servicing | Maintenance scope | Barry described the work as basically servicing the website; later indicated the client might use the old developer. | No amount stated. | Outcome uncertain.
24 Nov 2025 | Durachemgh.com | Servicing request | Domain shared and Barry described scope as servicing the website. | No amount stated. | No price/payment evidence.
24 Nov 2025 | Rosella.ng | Project identification | Rosella.ng shared in relation to a client meeting. | No amount stated. | Website/prototype project.
25 Nov 2025 | Rosella.ng / skincare site | Client feedback | Client wanted images replaced and domain purchased; team asked about next steps and client feedback. | No amount stated. | Scope update; domain/hosting not yet confirmed purchased.
30 Nov 2025 | Haulers Haven application | Project meeting | Another Haulers Haven meeting announced. | No amount stated. | Project activity.
1 Dec 2025 | Haulers Haven / Rosella / Maya skincare | Priority and scope | Barry said continue with the app; asked for image changes; prioritized Rosella; described another skincare business as a profile website with an articles page. | No amount stated. | Several separate projects referenced.
4 Dec 2025 | Rosella.ng | Prototypes shared | Two prototype links shared for client review. | No amount stated. | Prototype delivery.
8 Dec 2025 | Maya / Posh Beauty skincare website | Project kickoff | Simple skincare website requested for a Guinea business; Posh Beauty social links and meeting notes shared. | No amount stated. | Scope and references supplied.
10 Dec 2025 | Sow African Hair Braiding / Posh Beauty | Image/deployment changes | Sow image replacement requested; Posh Beauty image replacement and domain/hosting launch also discussed in nearby messages. | No amount stated. | Two distinct websites; keep records separate.
11 Dec 2025 | Posh Beauty / Maya skincare | Prototype and launch | posh-beauty.netlify.app shared; domain, hosting and launch discussed. | No price stated. | Prototype exists; launch/payment not confirmed.
11 Dec 2025 | John Maher website | New website / name pending | Client wanted a website but had not chosen a business name; email and SMS costs discussed. | SMS service cost not stated. | Requirements/quote pending.
26 Dec 2025 | Multiple prototypes/clients | Invoices sent | Barry said invoices had been sent and responses were pending; prototypes were expected to be built early the following month. | Amounts not stated. | General invoice status; not attributable to individual projects.
6 Jan 2026 | Haulers Haven application | External service renewal | Google Maps service had expired and needed renewal before implementation could continue. | Cost not stated. | Renewal needed; no payment confirmation.
11–12 Jan 2026 | Sow African Hair Braiding | Booking feature changes | Customers should book directly by tapping hairstyle/service images on service page and homepage. | No amount stated. | Scope change.
19 Jan 2026 | Haulers Haven application | Payment method removed | Sekou said Barry's bank card was removed from the project's backend. | No amount stated. | Administrative note; not a payment receipt.
21 Jan 2026 | Sow African Hair Braiding | Service pricing | Client requested hairstyle prices and service duration be added; Booksy link shared. | No amount stated. | Scope update.
21 Jan 2026 | Unspecified project/service | Payment promise | Barry said he would make a payment the following day and asked to use his business card for SMS service. Context does not unambiguously identify the payment. | Amount not stated. | Promise only; no receipt confirmation tied to this message.
22 Jan 2026 | Sow African Hair Braiding / SMS setup | Twilio credits | Team asked Barry to purchase credits; after setup discussion Barry said “C’est fait bro.” | Amount not stated. | Likely credits purchased; amount/transaction receipt absent.
24 Jan 2026 | Twilio / iBarry Marketing verification | Business URL submitted | ibarrymarketing.com used as terms-and-conditions URL during service verification; verification expected to take 2–3 days. | No amount stated. | Administrative setup.
27–28 Aug 2026 | Diallo Telly Institute app | Training inquiry | Client asked about training, but developer said the app had not been built and a process meeting was needed. | No amount stated. | Project not ready for training.

## Dev Team Payments
Date | Project / possible link | Amount | Currency | Payment evidence type | Evidence / interpretation
17 Nov 2025 | Website reactivation, likely AsmadGroup (confirm) | 800,000 GNF / one year | GNF | Quote | Sekou stated 800,000 GNF for one year after saying the client had not renewed the domain. | No receipt evidence; project association not fully explicit.
26 Dec 2025 | Multiple client projects | Amounts not stated | Not stated | Invoice status | Barry said invoices had been sent and responses were pending. | Not evidence of receipt; not attributable to a specific project.
6 Jan 2026 | Haulers Haven application | Amount not stated | Not stated | Renewal required | Google Maps service expired and needed renewal before implementation continued. | No proof of payment.
21 Jan 2026 | Unspecified project/service | Amount not stated | Not stated | Payment promised | Barry said he would make the payment tomorrow; adjacent messages concern SMS service and card usage, but project/amount are unclear. | Do not assign to a specific project without more context.
22 Jan 2026 | Likely Sow African Hair Braiding SMS setup | Amount not stated | Not stated | Credits purchase reported complete | After team asked Barry to buy Twilio credits, he said “C’est fait bro.” | Likely purchase completed, but no amount or receipt shown.

## All Projects Master
Project name | Dates evidenced in chats | Date range / coverage | Source chat(s) | Payment status summary | Scope / price summary | Notes on identity / duplicates
Bosswear website | 18 Nov 2025 | Nov 2025 | iBarry pricing chat | No confirmed payment in chat. Final price and whether project proceeded are unclear. | Initial pricing moved through $1,500, $1,200, $1,300, then Barry said he would charge client $1,500; on 18 Nov reduced request to $750 + $50 maintenance. On 19 Nov Barry offered to add $150 to the $750. | Existing record; see Project Register
Sow African Hair Braiding website | 20 Dec 2025 – 24 Feb 2026 | Dec 2025–Feb 2026 | iBarry pricing chat | No explicit payment receipt located. Website work and email/booking troubleshooting are documented. | 20 Dec: €60 domain + €70 hosting stated (message says €120 total/year, arithmetic mismatch). 12 Jan: $130 domain+hosting discussed. 15 Jan: $70 hosting if domain already owned; domain $60. | Existing record; see Project Register
Mother's Love HHC website | 8 Feb – 8 Jun 2026 | Feb–Jun 2026 | iBarry pricing chat | $250 is a request for money, not proof of receipt. $125 image is a payment-related clue, but not enough to confirm what it paid for. 3 Jun Barry said client had not paid him yet. | 5 Jun: Barry said he urgently needed $250 from the client. 6 May: Barry shared an image and wrote “This is $125”; surrounding context discusses Mother's Love domain, but purpose/recipient of the $125 is not explicit. Domain/hosting quote not clearly isolated from other work. | Existing record; see Project Register
LinZ / Fottal.com caregiving website | 27 Mar – 21 May 2026 | Mar–May 2026 | iBarry pricing chat | 3 Apr transfer explicitly acknowledged after Barry asked if it was received; amount/purpose not definitively tied to a specific quote. 16 May transfer explicitly acknowledged; amount unclear. 6 May $125 image is more likely in Mother's Love context and should not be assumed to be this project. | 3 Apr: labor amount discussed as 1,200,000 GNF (Barry) vs 1,250,000 GNF (Sekou). 29 Apr: 2,500,000 GNF labor + $120 domain/hosting quoted. Earlier figures conflict and are not reconciled. | Existing record; see Project Register
Unnamed client website / international expansion | 6–15 Mar 2026 | Mar 2026 | iBarry pricing chat | No payment or deposit receipt confirmed. Client/project identity is not clear from the chat. | 14 Mar: $3,500 price asked about and team reportedly accepted to avoid losing the client. 15 Mar: additional work/extension would have extra cost, not quantified. | Existing record; see Project Register
iBarry x Car Rental Platform | 15–18 Aug 2026 | Aug 2026 | iBarry pricing chat | No payment evidence identified. | No price explicitly captured in the visible messages summarized here. | Existing record; see Project Register
iBarry peer-to-peer application / service support | 18 Aug – 2 Oct 2026 | Aug–Oct 2026 | iBarry pricing chat | No confirmation that the $250 annual support fee was paid or that a final support contract was accepted. | 19 Sep: $250/year flat support fee proposed. Operational costs were to be separate. Client requested first 3 months free maintenance after completion plus training. | Existing record; see Project Register
Barry's personal real-estate domain | 8–15 Jun 2026 | Jun 2026 | iBarry pricing chat | Promised payment only; no receipt confirmation identified. | 10 Jun: $60 domain + $70 annual hosting = $130. Barry said he would send money on 11 Jun and again on 15 Jun. | Existing record; see Project Register
iBarryRealtor.com website | 19 Sep – 12 Oct 2026 | Sep–Oct 2026 | iBarry pricing chat | Final $500 agreement documented, but no actual payment receipt identified. The installment plan was proposed by Barry; payments not confirmed. $30/month is a recurring estimated operating cost, not confirmed paid. | 6 Oct: $800 quote; Barry countered $400; after negotiation final agreed development fee $500. Payment plan discussed: 60% when ready + 10% each Friday for 4 installments. Approx. $30/month for IDX/MLS was discussed separately. | Existing record; see Project Register
Haulers Haven application / platform | 28 Oct 2025 – 19 Jan 2026 | Oct 2025–Jan 2026 | Dev Team chat | No confirmed project-fee receipt. Barry said payment would be made the next day on 21 Jan (purpose unclear). On 22 Jan he said Twilio credits purchase was done after being asked to buy credits; amount not stated. | No project fee amount visible in this chat. Google Maps service expired 6 Jan 2026; renewal needed, amount not stated. Twilio/SMS service setup discussed Jan 2026. | Active development / payment unclear
iBarry Marketing website update | 1 Nov 2025 – 24 Jan 2026 | Nov 2025–Jan 2026 | Dev Team chat | No payment evidence in this chat. | No development price or payment stated in this chat. | Website update / payment not discussed
Fottal website (overlaps earlier Fottal/LinZ record) | 13 Nov 2025 – 21 May 2026 (combined evidence) | Nov 2025–May 2026 | Dev Team chat | No additional payment receipt identified in Dev Team chat. Use existing workbook's 3 Apr and 16 May 2026 receipt acknowledgements, amounts unclear. | Dev Team chat names Fottal on 13 Nov 2025 but no amount in this chat. Earlier iBarry pricing workbook has later price/payment details; see existing Fottal/LinZ project record. | Merged/overlapping project; avoid double-counting
Sow African Hair Braiding website | 14 Nov 2025 – 24 Feb 2026 (combined evidence) | Nov 2025–Feb 2026 | Dev Team chat | No confirmed payment receipt for the domain/hosting in Dev Team chat. On 22 Jan Barry said Twilio credits purchase was done; likely SMS credits, amount not stated. | Dev Team chat states domain renewal for 1 year as 800,000 GNF on 17 Nov, but context likely another site/reactivation and should not be assigned to Sow without confirmation. Earlier chat quoted domain/hosting in EUR/USD. | Active website work; payment unclear
AsmadGroup.com website reactivation / redesign | 17–20 Nov 2025 | Nov 2025 | Dev Team chat | No confirmed payment receipt. On 20 Nov Barry said Asmad Group was waiting for an urgent payment and wanted the domain functional. | 800,000 GNF for one year was quoted on 17 Nov in the preceding exchange; likely domain renewal/reactivation but chat context does not explicitly attach it beyond that site discussion. | Reactivation/possible redesign; payment unclear
Custom blazer e-commerce website (client unnamed) | 18 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence in this chat. | No price stated. | Requirements only / client identity unclear
Mr Al's e-commerce website | 21 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence in this chat. | No price stated. | Discovery/meeting only
Construction company website (client unnamed) | 21 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence in this chat. | No price stated. | Discovery only
Haulers Haven website servicing | 23–25 Nov 2025 | Nov 2025 | Dev Team chat | No payment receipt identified. | No price stated. Domain and hosting were to be discussed after client feedback; no amount captured. | Potentially separate servicing engagement; outcome unclear
Durachemgh.com website servicing | 24 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence in chat. | No price stated. | Servicing discussion only
Rosella.ng website / skincare brand | 24 Nov – 11 Dec 2025 | Nov–Dec 2025 | Dev Team chat | Barry said invoices had been sent and responses were pending on 26 Dec, but no specific payment receipt is linked to Rosella. | No price stated in Dev Team chat. | Prototype delivered; launch/payment unclear
Maya / Posh Beauty 224 skincare website | 1–11 Dec 2025 | Dec 2025 | Dev Team chat | No payment receipt identified. Invoices for clients generally were said to be sent 26 Dec, not specifically assigned to this project. | No price stated. | Prototype delivered; payment/launch unclear
John Maher website (business name undecided) | 11 Dec 2025 | Dec 2025 | Dev Team chat | No payment evidence identified. | No website fee stated. Paid SMS service required; exact service cost not stated. | Requirements/quote pending
Diallo Telly Institute app | 27–28 Aug 2026 | Aug 2026 | Dev Team chat | No payment evidence in chat. | No price stated. | Requirements/process not finalized
Skincare website / profile website (Maya meeting notes; likely Posh Beauty) | 1–8 Dec 2025 | Dec 2025 | Dev Team chat | No payment evidence. | No price stated. | Alias/identity linked with caveat
Haulers Haven website servicing | 23–25 Nov 2025 | Nov 2025 | Dev Team chat | No confirmed payment evidence | Servicing and domain/hosting discussed; client may have returned to old developer. | May be distinct from Haulers Haven app
Durachemgh.com website servicing | 24 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence | Servicing existing website. | Named website
Rosella.ng website | 24 Nov–11 Dec 2025 | Nov–Dec 2025 | Dev Team chat | Invoices reportedly sent generally; no receipt linked | Two prototypes shared 4 Dec; feedback pending. | Likely same as Rosella references in meeting notes
Custom blazer e-commerce website | 18 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence | Customizable blazer sales website. | May be Mr Al's e-commerce; unconfirmed
Mr Al's e-commerce website | 21 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence | Meeting discussed; scope not specified. | May be blazer site; unconfirmed
Construction company website (unnamed) | 21 Nov 2025 | Nov 2025 | Dev Team chat | No payment evidence | Discovery meeting planned; no price stated. | Client unnamed
John Maher website | 11 Dec 2025 | Dec 2025 | Dev Team chat | No payment evidence | Business name undecided; website and SMS costs discussed. | Business/brand name pending
Diallo Telly Institute app | 27–28 Aug 2026 | Aug 2026 | Dev Team chat | No payment evidence | Client asked about training; app had not yet been built. | Project status unclear
iBarry Marketing website update | 1 Nov 2025–24 Jan 2026 | Nov 2025–Jan 2026 | Dev Team chat | No payment evidence | Website content update and URL used for Twilio compliance. | May be maintenance/content update rather than new website build